## HPDI Project Plan
HPDI Project Plan
Tasks | Responsible Team | Status | Progress | Start Date | Target Date | Actual Date | Owner | Notes | Action Items
Planning
Project Charter
Develop Project Charter | Author | Complete | 100% |  | 2021-03-12 |  | Aisha Neal/Sarah Taylor
Approve Project Charter | Author | In Progress | 100% |  | 2021-03-24 | 2021-03-29 | Helena Rawson/Pam Bell Sarah Taylor/Chris Caudill | 3/29: Received approvals from compliance & sponsors. 3/23: Added an amendment to the project charter scope to include the CMS, ONC, & Metric requirements w/Task status: Closed - No Action, Open - Requires Action, Additional Core Clarification - Confirm w/Core. 3/22: Met & assigned DRIs to all CMS requirements Tasks [OQ-276 / OQ-277 / OQ-278]. 3/17: Contacted Compliance to follow-up on requirements/scope to approve project charter. Team decided a meeting was best to confirm; meeting scheduled 3/22 to discuss & review. 3/16: Received feedback from Compliance team & updates made; resent for review & waiting for response. 3/15: Sent Project Charter to Compliance team [Helena, Megan, Carlene] to review Scope verbiage; once confirmed routing for approval.
Stakeholder Register
Develop Stakeholder Register | Author | Complete | 100% |  | 2021-03-26 |  | Aisha Neal |  | Need Core to identify associates to assign to HPDI.
Identify RACI | Author | Complete | 100% |  | 2021-03-26 |  | Aisha Neal
RAID Log
Create RAID Log | Author | Complete | 100% |  | 2021-03-04 |  | Aisha Neal
Core VSR
Create VSR for Core Requirements | Author | Complete | 100% |  |  |  | Sarah Taylor | Include 5 MFs for Core CDF to deliver.
Approve VSR for Core Requirements | Author | Complete | 100% |  | 2021-03-26 | 2021-03-24 | Chris Caudill/Pam Bell | 3/24: Met & received approval from Pam for MF1, MF2, MF4 estimates provided by Core. [MF1: 1.75EM / $15,580; MF2: 12.38EM / $166,297; MF4: Estimate not yet provided so Sarah doubled Sonya's team estimate to use for MF4 so we do not have to go back & ask for funding again. Core will inform Author when the funding is in place.] 3/19: Pam requested Sateesh to add Core VSR as an agenda item to discuss at the Core IT Funding call 3/25. 3/10: Emailed VSR v3 to Chris & Pam for review/approval. 3/9: Business approval needed; Sarah sent VSR to Pam & Chris.
Assign Core PM to HPDI Project | Core | Complete | 100% |  |  | 2021-03-08 |  | Devender Vidhani assigned as Core PM.
Assign Business Owners for Core VSR | Core | Complete | 100% |  | 2021-03-26 | 2021-03-22 |  | MF1: DRIs - Sonya Ash, Kumar Kakani, Shivang Patel; requested date from Google 4/1 MF2: DRI - Shivang Patel; requested date from Google 4/22 MF3: DRI - Julia/Karen [Author owns], Sid Sehgal [Core Architect to run queries], Tim Sandman [Core Consultant] MF4: DRI - Shivang Patel MF5: DRI - Jennifer Vesole
Data Subjects
Member
Patient Demographics
Data Mapping
Author Provide Patient Demographics Sample Data to Maven Wave | Author | Complete | 100% |  |  |  | Sarah Taylor
Maven Wave Complete Plan Coverage Data Mapping | Maven Wave | Complete | 100% |  |  | 2021-04-12 | Dan Bouckaert
Author Data Steward Approve Data Mapping | Author | Complete | 100% |  | 2021-04-12 | 2021-04-15 | Corey Shaw | 4/15: Dan updated Data Mapping & Aisha sent back to Corey for review/approval. Corey provided approval. 4/14: Corey rejected Patient Demographic Data Mapping due to Marital Status is not a field for the member to fill out on the application so Core Enrollment defaults all of these Medicare records to Single. Sent Data Mapping back to Maven Wave to update. 4/13: Aisha sent Corey final Patient Demographic Data Mapping for review/approval. | Corey to provide approval through Teams by 4/14.
Review Final Patient Demographics Data Mapping | Author | Complete | 100% |  | 2021-04-20 |  | Catherine Luttmer | Confirm if any changes needed for UST.
Development
UST Complete Dev for Patient Demographics Publication | UST | Complete |  |  | 2021-04-30 |  | Suresh Nayak
Author Interop to Enrich/Subscribe | Author | In Progress | 100%% |  | 2021-05-07 |  | James Minks
Maven Wave Complete Dev for Patient Demographics | Maven Wave | In Progress |  |  | 2021-05-06 |  | Dan Bouckaert | 5/12: Date changed from 4/28 to 5/6. 4/28: Per Amita, MW Dev behind.
System Integration Testing
UST Complete SIT for Member Demographics | UST | Not Started |  | 2021-05-03 | 2021-05-21 |  | Suresh Nayak | UST will continue their SIT testing even after conditional sign-off.
Maven Wave Complete SIT for Member Demographics | Maven Wave | Not Started |  |  | 2021-05-21 |  | Dan Bouckaert | 5/12: Date changed from 5/11 to 5/21.
Author Interop Complete SIT Member Demographics | Author | Not Started |  |  | 2021-05-21 |  | Sarah Taylor | 4/16: Date will be 2 weeks from Author Interop to Enrich/Subscribe.
Author Complete End-to-End SIT | Author | Not Started |  | 2021-05-17 | 2021-05-21 |  | Robert Spielberger | 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
User Acceptance Testing
Author Develop UAT Test Plan | Author | In Progress |  |  | 2021-04-15 | 2021-04-22 | Yuliya Roberts | 4/16: Schedule project plan review session w/Robert Spielberger 4/19.
Author Complete UAT for Member Demographics | Author | Not Started |  | 2021-05-21 | 2021-06-10 |  | Yuliya Roberts | 5/6: UAT timeline Start Date 5/21 - End Date 6/10; functionality being delivered at different timeframes; testing soon as made available to team. 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
Plan Coverage
Data Mapping
Author Provide Plan Coverage Sample Data to Maven Wave | Author | Complete | 100% |  |  |  | Sarah Taylor
Maven Wave Complete Plan Coverage Data Mapping | Maven Wave | In Progress | 90% |  |  |  | Dan Bouckaert | 4/16: Per Wil, Data Mapping spreadsheet Payor field needs to be changed from Author by Humana to Humana.
Review Final Plan Coverage Data Mapping | Maven Wave/Author | In Progress | 50% |  | 2021-04-16 |  | Jay Goebel/Catherine Luttmer | 4/16: James to coordinate w/Engineering team to get Group ID added.
Author Data Steward Approved Final Data Mapping | Author | In Progress | 80% |  |  |  | William Tolbert | 5/3: Open question 4/19: MW made update & resent to Wil for approval. 4/16: Sent Wil approval request through Teams; rejected stating Payor name needs to be changed from Author by Humana to Humana.
Development
UST Complete Dev for Plan Coverage Publication | UST | In Progress |  |  | 2021-05-07 |  | Suresh Nayak
Author Interop to Enrich/Subscribe | Author | In Progress | 100% |  | 2021-05-07 |  | James Minks
Maven Wave Complete Dev for Plan Coverage | Maven Wave | In Progress |  |  | 2021-05-12 |  | Dan Bouckaert | 5/12: Date changed to 5/12.
System Integration Testing
UST Complete SIT for Plan Coverage | UST | Not Started |  |  | 2021-05-21 |  | Suresh Nayak
Maven Wave Complete SIT for Plan Coverage | Maven Wave | Not Started |  |  | 2021-05-21 |  | Dan Bouckaert | 5/12: Date changed from 5/17 to 5/12.
Author Interop Complete SIT for Plan Coverage | Author | Not Started |  |  | 2021-05-21 |  | Sarah Taylor | 4/16: Date will be 2 weeks from Author Interop to Enrich/Subscribe.
Author Complete End-to-End SIT | Author | Not Started |  | 2021-05-17 | 2021-05-21 |  | Robert Spielberger | 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
User Acceptance Testing
Author Develop UAT Test Plan | Author | In Progress |  |  | 2021-04-15 | 2021-04-22 | Yuliya Roberts | 4/16: Schedule project plan review session w/Robert Spielberger 4/19.
Author Complete UAT for Plan Coverage | Author | Not Started |  | 2021-05-21 | 2021-06-10 |  | Yuliya Roberts | 5/6: UAT timeline Start Date 5/21 - End Date 6/10; functionality being delivered at different timeframes; testing soon as made available to team. 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
PCP
Data Mapping
Author Provide PCP Sample Data to Maven Wave | Author | Complete | 100% |  |  |  | Sarah Taylor
Maven Wave Complete PCP Data Mapping | Maven Wave | In Progress | 90% |  | 2021-04-23 |  | Dan Bouckaert
Review Final PCP Data Mapping | Maven Wave/Author | In Progress | 50% |  | 2021-05-03 |  | Jay Goebel/Catherine Luttmer
Author Data Steward Approved Final Data Mapping | Author | In Progress | 80% |  | 2021-05-07 |  | William Tolbert
Development
UST Complete Dev for PCP Publication | UST | In Progress |  |  | 2021-05-14 |  | Suresh Nayak
Author Interop to Enrich/Subscribe | Author | In Progress | 100% |  | 2021-05-07 |  | James Minks
Maven Wave Complete Dev for PCP | Maven Wave | Not Started |  |  | 2021-05-11 |  | Dan Bouckaert
System Integration Testing
UST Complete SIT for PCP | UST | Not Started |  |  | 2021-05-21 |  | Suresh Nayak
Maven Wave Complete SIT for PCP | Maven Wave | Not Started |  |  | 2021-05-26 |  | Dan Bouckaert
Author Interop Complete SIT for PCP | Author | Not Started |  |  | 2021-05-21 |  | Sarah Taylor
Author Complete End-to-End SIT | Author | Not Started |  | 2021-05-17 | 2021-05-21 |  | Robert Spielberger
User Acceptance Testing
Author Develop UAT Test Plan | Author | In Progress |  |  | 2021-04-15 | 2021-04-22 | Yuliya Roberts
Author Complete UAT for PCP | Author | Not Started |  | 2021-05-21 | 2021-06-10 |  | Yuliya Roberts | 5/6: UAT timeline Start Date 5/21 - End Date 6/10; functionality being delivered at different timeframes; testing soon as made available to team.
Provider
Practitioner
Data Mapping
Author Provide Practitioner Sample Data to Maven Wave | Author | Complete | 100% |  | 2021-03-15 |  | Sarah Taylor
Maven Wave Complete PCP Data Mapping | Maven Wave | Complete | 100% |  | 2021-04-12 |  | Dan Bouckaert
Review Final Practitioner Data Mapping | Author | Complete | 100% |  | 2021-04-22 |  | Catherine Luttmer/Jay Goebel
Author Data Steward Approve Data Mapping | Author | Complete | 100% |  | 2021-04-30 | 2021-05-04 | Emily Cariaganis/Michael Thompson | 5/4: Received approval from Emily. 5/3: Sent Final Data Mapping spreadsheet to Michael & Emily requesting approval by EOD 5/4.
Development
UST Complete Dev for PCP Publication | UST | In Progress |  |  | 2021-05-14 |  | Suresh Nayak
Author Interop Complete Dev for Practitioner | Author | Complete | 100% |  | 2021-05-07 |  | James Minks
Maven Wave Complete Dev for Practitioner | Interop | In Progress |  |  | 2021-05-06 |  | Dan Bouckaert | 5/12: Date changed from 4/27 to 5/6.
System Integration Testing
UST Complete SIT for Practitioner | UST | Not Started |  |  | 2021-05-21 |  | Suresh Nayak
Maven Wave Complete SIT for Practitioner | Maven Wave | Not Started |  |  | 2021-05-21 |  | Dan Bouckaert | 5/12: Date changed from 5/17 to 5/21. 5/11: Per Amita, for MW to start SIT testing they need Google to resolve issues with the HPDI tool. Once the issues are resolved, will have more concrete dates; hoping to resolve them this week.
Author Interop Complete SIT for Practitioner | Author | Not Started |  |  | 2021-05-21 |  | Sarah Taylor
Author Complete End-to-End SIT | Author | Not Started |  |  | 2021-05-31 |  | Robert Spielberger | 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
User Acceptance Testing
Author Develop UAT Test Plan | Author | In Progress |  |  | 2021-04-15 | 2021-04-22 | Yuliya Roberts | 4/16: Schedule project plan review session w/Robert Spielberger 4/19.
Author Complete UAT for PCP | Author | Not Started |  | 2021-05-21 | 2021-06-10 |  | Yuliya Roberts | 5/6: UAT timeline Start Date 5/21 - End Date 6/10; functionality being delivered at different timeframes; testing soon as made available to team. 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
Organization
Data Mapping
Author Provide PCP Sample Data to Maven Wave | Author | Complete | 100% |  | 2021-03-15 |  | Sarah Taylor
Maven Wave Complete PCP Data Mapping | Maven Wave | In Progress | 90% |  | 2021-04-12 |  | Dan Bouckaert
Review Final Organization Data Mapping | Maven Wave/Author | Complete | 100% |  | 2021-04-22 |  | Jay Goebel/Catherine Luttmer
Author Data Steward Approved Final Data Mapping | Author | Complete |  |  | 2021-04-30 | 2021-05-04 | Emily Cariaganis/Michael Thompson | 5/4: Received approval from Emily. 5/3: Sent Final Data Mapping spreadsheet to Michael & Emily requesting approval by EOD 5/4.
Development
Author Interop Complete Dev for Organization | Author | In Progress | 100% |  | 2021-05-14 |  | James Minks | 5/6: Per Bala, date changed from 5/7 to 5/14.
Maven Wave Complete Dev for Organization | Interop | Not Started |  |  | 2021-05-06 |  | Dan Bouckaert | 5/12: Date changed from 4/27 to 5/6.
System Integration Testing
UST Complete SIT for PCP | UST | Not Started |  |  | 2021-06-04 |  | Suresh Nayak
Maven Wave Complete SIT for Organization | Maven Wave | Not Started |  |  | 2021-05-21 |  | Dan Bouckaert | 5/12: Date changed from 5/17 to 5/21. 5/11: Per Amita, for MW to start SIT testing they need Google to resolve issues with the HPDI tool. Once the issues are resolved, will have more concrete dates; hoping to resolve them this week.
Author Interop Complete SIT for Organization | Author | Not Started |  |  | 2021-05-21 |  | Sarah Taylor
Author Complete End-to-End SIT | Author | Not Started |  |  | 2021-06-14 |  | Robert Spielberger | 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
User Acceptance Testing
Author Develop UAT Test Plan | Author | In Progress |  |  | 2021-04-15 | 2021-04-22 | Yuliya Roberts | 4/16: Schedule project plan review session w/Robert Spielberger 4/19.
Author Complete UAT for Organization | Author | Not Started |  | 2021-05-21 | 2021-06-10 |  | Yuliya Roberts | 5/6: UAT timeline Start Date 5/21 - End Date 6/10; functionality being delivered at different timeframes; testing soon as made available to team. 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
Medical Claims
Adjudicated Claims [Medical], Capitated Encounter Data, Provider Payment & Member Cost [Actual Cost Medical]
Data Mapping
Author Provide Medical Claims Sample Data to Maven Wave | Author | Complete | 100%
Maven Wave Complete Data Mapping | Maven Wave | In Progress | 90% |  | 2021-04-23 |  | Dan Bouckaert
Review Final Medical Claims Data Mapping | Maven Wave/Author | In Progress | 90% |  | 2021-04-28 |  | Jay Goebel/Catherine Luttmer
Author Data Steward Approved Final Data Mapping | Author | Not Started |  |  | 2021-04-23 |  | Nikki Woodcox | 5/12: Date changed from 4/23 to 5/11.
Development
Maven Wave Dev for Claims Data to FHIR Format | Maven Wave | Not Started |  |  | 2021-05-21 |  | Dan Bouckaert | 5/12: Date changed from 5/7 to 5/21.
Author Interop Build Dataflow to pass Claims JSON to Drop Zone | Author | In Progress | 50% |  | 2021-05-14 |  | Sarah Taylor | 5/6: Per Bala, date changed from 5/7 to 5/14. 4/28 [jrm] As per Bala, HRP (Claims<<<Where I left off on 4/27, Provider, Member, MemPractitioner, MemCoverage) Dev complete by Sprint 2 (05/07) 4/16: James confirm date for PI Planning 4/16.
System Integration Testing
Maven Wave Complete SIT for Medical Claims | Maven Wave | Not Started |  |  | 2021-05-28 |  | Dan Bouckaert | 5/12: Date changed from 5/17 to 5/28. 5/11: Per Amita, for MW to start SIT testing they need Google to resolve issues with the HPDI tool. Once the issues are resolved, will have more concrete dates; hoping to resolve them this week.
Author Interop Complete SIT for Medical Claims | Author | Not Started |  |  | 2021-05-21 |  | Sarah Taylor | 4/16: Date will be 2 weeks from Author Interop to Enrich/Subscribe.
Author Complete End-to-End SIT | Author | Not Started |  |  | 2021-05-27 |  | Robert Spielberger | 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
User Acceptance Testing
Author Develop UAT Test Plan | Author | In Progress |  |  | 2021-04-15 | 2021-04-22 | Yuliya Roberts | 4/16: Schedule project plan review session w/Robert Spielberger 4/19.
Author Complete UAT for Medical Claims | Author | Not Started |  | 2021-05-21 | 2021-06-10 |  | Yuliya Roberts | 5/6: UAT timeline Start Date 5/21 - End Date 6/10; functionality being delivered at different timeframes; testing soon as made available to team. 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
Procedures
Data Mapping
Author Provide Procedures Sample Data to Maven Wave | Author | Complete | 100% |  |  |  | Sarah Taylor
Maven Wave Complete Data Mapping | Maven Wave | In Progress | 75% |  | 2021-04-23 |  | Dan Bouckaert | 5/3: Missing MRM data. Author/MW level of understanding/scope on additional sources files (MRM). Scoping discussion to be scheduled for 5/4. Impact: need MRM files finalized by 5/7 for upcoming development activities.
Review Final Procedures Data Mapping | Maven Wave/Author | In Progress | 50% |  | 2021-04-28 |  | Jay Goebel/ Catherine Luttmer
Author Data Steward Approve Final Data Mapping | Author | Not Started |  |  | 2021-05-13 |  | Nikki Woodcox | 5/12: Date changed from 5/7 to 5/13.
Development
Core MRM Procedures Data Publication from CDF | Core | Complete | 100% |  | 2021-05-07 | 2021-05-10 | Shivang Patel | 5/10: Devender provided CR-51 delivery timeline [DEV Readiness 5/7, SIT Readiness 5/14, EXTQA Readiness 5/24, Targeted PROD Date 6/7]. 4/27: Per Shivang, targeting 4/30 to provide estimates & delivery timeline for CR-51. 4/23: CR-51 created for 6 addl MRM data publications [Care Team, Narrative Extract, Plan Care, Problems, Procedures, Goals].
Maven Wave Dev for Procedures | Maven Wave | Not Started |  |  | 2021-05-13 |  | Dan Bouckaert | 5/12: Date changed from 5/7 to 5/13.
Author Interop Dev for Procedures | Author | In Progress |  |  | 2021-05-21 |  | James Minks | 4/16: James confirm date for PI Planning 4/16. 4/26 [jrm] - MRM DEV complete by Sprint 3 (05/21)
System Integration Testing
Maven Wave Complete SIT for Procedures | Maven Wave | Not Started |  |  | 2021-05-20 |  | Dan Bouckaert | 5/12: Date changed from 5/17 to 5/20. 5/11: Per Amita, for MW to start SIT testing they need Google to resolve issues with the HPDI tool. Once the issues are resolved, will have more concrete dates; hoping to resolve them this week.
Author Interop Complete SIT for Procedures | Author | Not Started |  |  | 2021-05-21 |  | Sarah Taylor | 4/16: Date will be 2 weeks from Author Interop to Enrich/Subscribe.
Author Complete End-to-End SIT | Author | Not Started |  |  | 2021-05-27 |  | Robert Spielberger | 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
User Acceptance Testing
Author Develop UAT Test Plan | Author | In Progress |  |  | 2021-04-15 | 2021-04-22 | Yuliya Roberts | 4/16: Schedule project plan review session w/Robert Spielberger 4/19.
Author Complete UAT for Procedures | Author | Not Started |  | 2021-05-21 | 2021-06-10 |  | Yuliya Roberts | 5/6: UAT timeline Start Date 5/21 - End Date 6/10; functionality being delivered at different timeframes; testing soon as made available to team. 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
Pharmacy Claims: Adjudicated Claims [Pharmacy], Provider Payment & Member Cost [Actual Cost Pharmacy]
Data Mapping
Author Provide Medical Claims Sample Data to Maven Wave | Author | Complete | 100% |  |  |  | Sarah Taylor
Maven Wave Complete Data Mapping | Maven Wave | In Progress | 90% |  | 2021-04-23 |  | Dan Bouckaert
Review Final Rx Claims Data Mapping | Maven Wave/Author | Complete | 100% |  | 2021-04-28 | 2021-05-11 | Jay Goebel/Catherine Luttmer
Author Data Steward Approve Final Data Mapping | Author | Complete | 100% |  | 2021-04-23 | 2021-05-12 | Mary Sanders/Melissa Nemtsov | 5/12: Received approval from Mary, Melissa & Pam. 5/11: Sent to Data Stewards for review & approval; targeting 5/12 by noon. 4/30: Informed MW targeting Data Steward approval 5/3. 4/26: Approved date changed to 4/28.
Development
Core Deploy Rx EOB API in QA | Core | Complete | 100% |  | 2021-04-01 | 2021-04-09 | Sanath Kutumbaka
Maven Wave Integrate Rx Claims Dev to HPDI | Maven Wave | Not Started |  |  | 2021-05-21 |  | Dan Bouckeart | 5/12: Date changed from 5/7 to 5/21.
Author Interop Batch Rx Claims Dev to HPDI | Author | Not Started |  |  | 2021-05-21 |  | Sarah Taylor | 4/28 [jrm] As per Bala, EOB Rx Claims - Dev complete by Sprint 3 (05/21)
System Integration Testing
Maven Wave Complete SIT for Rx Claims | Maven Wave | Not Started |  |  | 2021-05-28 |  | Dan Bouckeart | 5/12: Date changed from 6/4 to 5/28. 5/11: Per Amita, for MW to start SIT testing they need Google to resolve issues with the HPDI tool. Once the issues are resolved, will have more concrete dates; hoping to resolve them this week.
Author Interop Complete SIT for Rx Claims | Author | Not Started |  |  | 2021-06-04 |  | Sarah Taylor
Author Complete End-to-End SIT | Author | Not Started |  |  | 2021-06-10 |  | Robert Spielberger | 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
User Acceptance Testing
Author Develop UAT Test Plan | Author | In Progress |  |  | 2021-04-15 | 2021-04-22 | Yuliya Roberts
Author Complete UAT for Rx Claims | Author | Not Started |  | 2021-05-21 | 2021-06-10 |  | Yuliya Roberts | 5/6: UAT timeline Start Date 5/21 - End Date 6/10; functionality being delivered at different timeframes; testing soon as made available to team. 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
Medications
Medications
Data Mapping
Finalize Data Sources | Author | In Progress |  |  | 2021-04-13 |  | Mary Sanders
Author Provide Sample Data to Maven Wave | Author | Complete | 100% |  | 2021-04-12 | 2021-05-07 | Mary Sanders | 4/22: MW communicated drop dead date of 5/7. 4/12: Author completed sample data for MRM data source but need confirmation on the others [Medical Claims/Rx Claims/OML]. 3/26: MW changed due date from 3/30 to 4/12 [drop dead date]. 3/19: Pam transitioned Data Steward role to Mary Sanders.
Maven Wave Complete Data Mapping | Maven Wave | In Progress | 90% |  | 2021-04-26 |  | Dan Bouckaert | 5/3: Initial Review session conducted; next step Subsequent Review by Jay.
Review Final Medications Data Mapping | Maven Wave/Author | In Progress |  |  | 2021-04-30 |  | Jay Goebel/Catherine Luttmer
Author Data Steward Approve Final Medication Data Mapping | Author | Not Started |  |  | 2021-05-13 |  | Mary Sanders | 5/12: Date changed from 5/7 to 5/13.
Development
Core Expose Medication API | Core | Complete | 100% | 2021-04-29 | 2021-05-07 | 2021-05-10 | Sonya Ash | 5/7: Per Devender, Medication API exposed to QA environment. Author team to move forward w/testing. Note: QA Sign-off is expected by 5/14 to meet PROD deployment date of 5/25. 4/30: Core provided delivery timelines & estimates; received funding approval for CR-52. 4/23: CR-52 created; need Core estimates & funding approval to determine delivery timeline.
Maven Wave Complete Dev for Medications | Maven Wave | Not Started |  |  | 2021-05-20 |  | Dan Bouckeart
Author InterOp Provide Data to Drop Zone | Author | Not Started |  |  | 2021-06-04 |  | Sarah Taylor | [jrm] 4/28: As per Bala, Medications - Not yet slated to a sprint yet (plan bw Sprint 3/4)
System Integration Testing
Author Complete EXTQA Readiness for Medication API | Author | Not Started |  |  |  | 2021-05-14 | Sankunthala Matlapudi | 5/12: Per Devender, requesting Author to provide QA sign-off by 5/14 to help Core plan Prod deployment by 5/25 for API.
Maven Wave Complete SIT for Medications | Maven Wave | Not Started |  |  | 2021-05-25 |  | Dan Bouckaert | 5/12: Date changed from 6/2 to 5/25. 5/11: Per Amita, for MW to start SIT testing they need Google to resolve issues with the HPDI tool. Once the issues are resolved, will have more concrete dates; hoping to resolve them this week.
Author Interop Complete SIT for Medications | Author | Not Started |  |  | 2021-06-15 |  | Sarah Taylor
Author Complete End-to-End SIT | Author | Not Started |  |  | 2021-06-22 |  | Robert Spielberger | 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
User Acceptance Testing
Author Develop UAT Test Plan | Author | In Progress |  | 2021-04-15 | 2021-04-22 |  | Yuliya Roberts
Author Complete UAT for Medications | Author | Not Started |  | 2021-05-21 | 2021-06-10 |  | Yuliya Roberts | 5/6: UAT timeline Start Date 5/21 - End Date 6/10; functionality being delivered at different timeframes; testing soon as made available to team. 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
Drug Formularies
Data Mapping
Maven Wave Complete Data Mapping | Maven Wave | In Progress | 50% |  | 2021-04-28 |  | Dan Bouckeart
Review Final Drug Formularies Data Mapping | Maven Wave/Author | In Progress | 75% |  | 2021-05-05 |  | Jay Goebel/Catherine Luttmer
Author Data Steward Approve Final Data Mapping | Author | Not Started |  |  | 2021-05-13 |  | Mary Sanders/Melissa Nemtsov | 5/12: Date changed from 5/7 to 5/13.
Development
Core Complete Dev for Drug Formularies | Core | Complete |  |  | 2021-04-09
Author Interop Complete Dev for Drug Formularies | Author | Not Started |  |  | 2021-05-21 |  | Sarah Taylor | [jrm] 4/28: As per Bala, Drug Formulary - Dev complete by Sprint 3 (05/21
Maven Wave Complete Dev for Drug Formularies | Maven Wave | Not Started |  |  | 2021-05-17 |  | Dan Bouckeart | 5/12: Date changed from 5/30 to 5/17.
System Integration Testing
Maven Wave Complete SIT for Drug Formularies | Maven Wave | Not Started |  |  | 2021-05-25 |  | Dan Bouckaert | 5/12: Date changed from 6/2 to 5/25. 5/11: Per Amita, for MW to start SIT testing they need Google to resolve issues with the HPDI tool. Once the issues are resolved, will have more concrete dates; hoping to resolve them this week.
Author Interop Complete SIT for Drug Formularies | Author | Not Started |  |  | 2021-06-04 |  | Sarah Taylor
Author Complete End-to-End SIT | Author | Not Started |  | 2021-06-05 | 2021-06-11 |  | Robert Spielberger | 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
User Acceptance Testing
Author Develop UAT Test Plan | Author | In Progress |  | 2021-04-15 | 2021-04-22 |  | Yuliya Roberts
Author Complete UAT for Drug Formularies | Author | Not Started |  | 2021-05-21 | 2021-06-10 |  | Yuliya Roberts | 5/6: UAT timeline Start Date 5/21 - End Date 6/10; functionality being delivered at different timeframes; testing soon as made available to team. 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
Provider & Pharmacy Directory
Development
Maven Wave Create Proof of Concept | Maven Wave | Complete | 100% |  | 2021-04-23 |  | Dan Bouckeart | 4/23: Conducted demo for Proof of Concept.
Core Deploy Endpoint in QA | Core | Not Started |  |  | 2021-05-30 |  | Jennifer Vesole | 5/3: Core experiencing slight delay receiving data by 4/30 but confirmed it will not affect timeline providing to Author by 5/30.
Maven Wave Proxy Build to QA Endpoint | Maven Wave | Not Started |  |  | 2021-06-03 |  | Dan Bouckeart
System Integration Testing
Maven Wave Complete SIT for Provider & Pharmacy Directory | Maven Wave | Not Started |  |  | 2021-06-10 | ~6/1/2021 | Dan Bouckeart | 5/11: Per Amita, for MW to start SIT testing they need Google to resolve issues with the HPDI tool. Once the issues are resolved, will have more concrete dates; hoping to resolve them this week.
Author Complete End-to-End SIT | Author | Not Started |  |  | 2021-06-16 |  | Robert Speilberger | 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
User Acceptance Testing
Author Develop UAT Test Plan | Author | In Progress |  | 2021-04-15 | 2021-04-22 |  | Yuliya Roberts
Author Complete UAT for Provider & Pharmacy Directory | Author | Not Started |  | 2021-05-21 | 2021-06-10 |  | Yuliya Roberts | 5/6: UAT timeline Start Date 5/21 - End Date 6/10; functionality being delivered at different timeframes; testing soon as made available to team. 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
Clinical
Sugar Data: Opportunities, Goals, Problems | [7 empty] | Opporutnities include Assessment & Plan of Treatment. Problems include Health Concerns.
Data Mapping
Author Provide Sample Data to Google & Maven Wave | Author | Complete | 100% |  | 2021-03-15 | 2021-03-04 | Sarah Taylor
Maven Wave Complete Data Mapping | Maven Wave | In Progress | 50% |  | 2021-04-19 |  | Dan Bouckeart | 5/3: Initial Review conducted. Missing MRM data. Author/MW level of understanding/scope on additional sources files (MRM). Scoping discussion to be scheduled for 5/4. Impact: Need MRM files finalized by 5/7 for upcoming development activities.
Review Final Sugar Data Mapping | Maven Wave/Author | In Progress | 75% |  | 2021-04-30 |  | Jay Goebel/Catherine Luttmer | 5/7: Sugar mapping is at a standstill due to the condition identifier attribute --Author needs to understand how this is being used in the HPDI overall design before we can determine what we have mapped is correct. Bonnie is working to get us a call set up with the right googlers to get this nailed down later today.
Author Data Steward Approve Final Sugar Data Mapping | Author | Not Started |  |  | 2021-05-07 |  | Chris Caudill/Aaron Kerr
Development
Core MRM Data Publication from CDF | Core | In Progress | 100% |  | 2021-05-07 | 2021-05-10 | Shivang Patel | 5/10: Devender provided CR-51 delivery timeline [DEV Readiness 5/7, SIT Readiness 5/14, EXTQA Readiness 5/24, Targeted PROD Date 6/7]. 4/30: Core provided delivery timeline for CR-51 except MF6: Historic Load & Narrative Extract. 4/27: Per Shivang, targeting 4/30 to provide estimates & delivery timeline for CR-51. 44/23: CR-51 created for 6 addl MRM data publications [Care Team, Narrative Extract, Plan Care, Problems, Procedures, Goals].
Maven Wave Complete Sugar Dev | Maven Wave | Not Started |  |  | 2021-04-30 |  | Dan Bouckeart
Extract Sugar Data | Sugar | Complete | 100% |  | 2021-05-07 | 2021-05-10 | Noel Winslow | 5/10: Brian confirmed issue w/file naming convention resolved & code is in SIT. 5/7: Per Noel, the DEV team ran into an issue where files were overwriting each other so need to change the Ymd format in the file names to something like Ymd-Hisu [Example: Opportunity-20210506-172544021912.csv]. [jrm] 4/28: As per Bala, Sugar (Goals, Problems, Opportunities) - Dev complete by Sprint 2 (05/07)
Author Interop Complete Dev for MRM Sugar Data | Author | In Progress |  |  | 2021-05-21 |  | Sarah Taylor | 5/3: Includes Goals, Problems & Plan Cares [Opportunities]
System Integration Testing
Core Complete SIT for MRM Data Publication | Core | In Progress |  |  | 2021-05-14 |  | Devender Vidhani | 5/12: Sarah requested Core to provide demo 5/14.
Maven Wave Complete SIT for Sugar | Maven Wave | Not Started |  |  | 2021-05-18 | ~6/1/2021 | Dan Bouckaert | 5/11: Per Amita, for MW to start SIT testing they need Google to resolve issues with the HPDI tool. Once the issues are resolved, will have more concrete dates; hoping to resolve them this week.
Author Interop Complete SIT for Sugar | Author | Not Started |  |  | 2021-05-21 |  | Sarah Taylor
Author Interop Complete EXTQA Readiness for MRM Data Publication | Author | Not Started |  |  | 2021-05-24 |  | Sankunthala Matlapudi
Author Complete End-to-End SIT | Author | Not Started |  |  | 2021-05-28 |  | Robert Spielberger | 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
User Acceptance Testing
Author Develop UAT Test Plan | Author | In Progress |  | 2021-04-15 | 2021-04-22 |  | Yuliya Roberts
Author Complete UAT for Sugar Data | Author | Not Started |  | 2021-05-21 | 2021-06-10 |  | Yuliya Roberts | 5/6: UAT timeline Start Date 5/21 - End Date 6/10; functionality being delivered at different timeframes; testing soon as made available to team. 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
Immunizations
Data Mapping
Provide Sample Data to Google & Maven Wave | Author | Complete | 100% |  | 2021-03-15 | 2021-03-12 | Karen Kinzel
Maven Wave Complete Draft Data Mapping | Maven Wave | In Progress | 90% |  | 2021-04-23 |  | Dan Bouckeart
Author Tech Review Approved Data Mapping | Maven Wave/Author | In Progress | 90% |  | 2021-04-30 |  | Jay Goebel/Catherine Luttmer
Author Data Steward Approve Final Data Mapping | Author | Not Started |  |  | 2021-05-05 |  | Karen Kinzel
Development
Core Expose Immunization API | Core | In Progress |  | 2021-05-07 | 2021-05-14 |  | Sonya Ash | 5/12: Per Devender, will be accessible in EXTQA environment to Author Interops team sometime by tomorrow 5/13. Requesting Author to provide QA sign-off by 5/14 to help Core plan Prod deployment by 5/25 for API. 4/30: Core provided delivery timelines & estimates; received funding approval for CR-52. 4/23: CR-52 created; need Core estimates & funding approval to determine delivery timeline.
Maven Wave Dev Complete for Immunizations | Maven Wave | Not Started |  |  | 2021-05-11 |  | Dan Bouckeart
Author Interop Dev Complete for Immunizations | Author | Not Started |  |  | 2021-06-04 |  | Sarah Taylor | 4/26: Per Bala, not yet slated to a Sprint [plan bw Sprint 3/4].
System Integration Testing
Author Complete EXTQA Readiness for Medication API | Author | Not Started |  |  |  | 2021-05-14 | Sankunthala Matlapudi | 5/12: 5/12: Per Devender, requesting Author to provide QA sign-off by 5/14 to help Core plan Prod deployment by 5/25 for API.
Maven Wave Complete SIT for Immunizations | Maven Wave | Not Started |  |  | 2021-05-26 | ~6/1/2021 | Dan Bouckeart | 5/11: Per Amita, for MW to start SIT testing they need Google to resolve issues with the HPDI tool. Once the issues are resolved, will have more concrete dates; hoping to resolve them this week.
Author Interop Complete SIT for Immunizations | Author | Not Started |  |  | 2021-06-15 |  | Sarah Taylor
Author Complete End-to-End SIT | Author | Not Started |  |  | 2021-06-18 |  | Robert Spielberger | 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
User Acceptance Testing
Author Develop UAT Test Plan | Author | In Progress |  | 2021-04-15 | 2021-04-22 |  | Yuliya Roberts
Author Complete UAT for Immunizations | Author | Not Started |  | 2021-05-21 | 2021-06-10 |  | Yuliya Roberts | 5/6: UAT timeline Start Date 5/21 - End Date 6/10; functionality being delivered at different timeframes; testing soon as made available to team. 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
Labs & Vital Signs
Data Mapping
Author Provide Sample Data to Google & Maven Wave | Author | Complete | 100% |  |  |  | Karen Kinzel
Maven Wave Complete Data Mapping | Maven Wave | In Progress | 90% |  | 2021-04-26 |  | Dan Bouckeart
Review Final Labs & Vital Signs Data Mapping | Maven Wave/Author | In Progress | 90% |  | 2021-05-04 |  | Jay Goebel/Catherine Luttmer
Author Data Steward Approve Final Data Mapping | Author | Not Started |  |  | 2021-05-05 |  | Karen Kinzel
Development
Author Interop Dev Complete Observation API | Author | Not Started |  |  | 2021-05-21 |  | Sarah Taylor | [jrm] 4/28: As per Bala, Observations (Lab & Vital Signs) - Dev complete by Sprint 3 (05/21)
Maven Wave Dev Complete for Observation API | Maven Wave | Not Started |  |  | 2021-05-21 |  | Dan Bouckeart
System Integration Testing
Maven Wave Complete SIT for Observation API | Maven Wave | Not Started |  |  | 2021-05-28 | ~6/1/2021 | Dan Bouckeart | 5/11: Per Amita, for MW to start SIT testing they need Google to resolve issues with the HPDI tool. Once the issues are resolved, will have more concrete dates; hoping to resolve them this week.
Author Interop Complete SIT for Observation API | Author | Not Started |  |  | 2021-06-04 |  | Sarah Taylor
Author Complete End-to-End SIT | Author | Not Started |  | 2021-05-17 | 2021-06-09 |  | Robert Spielberger | 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
User Acceptance Testing
Author Develop UAT Test Plan | Author | In Progress |  | 2021-04-15 | 2021-04-22 |  | Yuliya Roberts
Author Complete UAT for Observation API | Author | Not Started |  | 2021-05-21 | 2021-06-10 |  | Yuliya Roberts | 5/6: UAT timeline Start Date 5/21 - End Date 6/10; functionality being delivered at different timeframes; testing soon as made available to team. 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
Care Team
Data Mapping
Author Provide Sample Data to Maven Wave | Author | Complete | 100% |  | 2021-03-15 | 2021-04-23 |  | 4/23: Sarah sent sample files to MW.
Author Complete Data Mapping | Author | Complete | 100% |  | 2021-04-14 |  | Chris Caudill | 3/26: Removed from list of MRM data topics; coming from Core's Observations API. 3/12: Per Sarah, sample data & schema uploaded.
Author Complete Blueprint | Author | Complete | 100% |  | 2021-04-16 | 2021-04-22 | Tim Doyle | Included in PI7 Sprint 3 4/23: James follow-up w/Sarah or Tim by EOD. Tim D said that this was completed as of 4/22.
Maven Wave Complete Data Mapping | Maven Wave | In Progress | 80% |  | 2021-04-23 |  | Dan Bouckeart | 5/3: Initial Review conducted. Missing MRM data. Author/MW level of understanding/scope on additional sources files (MRM). Scoping discussion to be scheduled for 5/4. Impact: Need MRM files finalized by 5/7 for upcoming development activities.
Review Final Care Team Data Mapping | Maven Wave/Author | Not Started |  |  | 2021-04-30 |  | Jay Goebel/ Catherine Luttmer
Author Data Stewards Approve Final Data Mapping | Author | Not Started |  |  | 2021-05-07 |  | Chris Caudill
Development
Core MRM Care Team Data Publication from CDF | Core | Complete | 100% |  | 2021-05-07 | 2021-05-10 | Shivang Patel | 5/10: Shivang provided CR-51 delivery timeline [DEV Readiness 5/7, SIT Readiness 5/14, EXT QA Readiness 5/24, Targeted PROD Date 6/7]. 4/27: Per Shivang, targeting 4/30 to provide estimates & delivery timeline for CR-51. 4/23: CR-51 created for 6 addl MRM data publications [Care Team, Narrative Extract, Plan Care, Problems, Procedures, Goals].
Maven Wave Complete Dev for Care Team | Maven Wave | Not Started |  |  | 2021-05-11 |  | Dan Bouckeart
Author Interop Complete Dev for Nexus [AssociateEntity/Relationship] | Author | Not Started |  |  | 2021-05-14 |  | Sarah Taylor | 5/6: Per Bala, date changed from 5/7 to 5/14. [jrm] 4/27: As per Bala MRM (Allergies, CareTeams, Goals, NarrativeExtract (ClincalNotes), PlanCares, Problems, Procedures) - Dev complete by Sprint 3 (05/21) - Nexus (AssociateEntity, Relationship) - Dev complete by Sprint 2 (05/07) 4/23: James will provide date by EOD.
Author Interop Complete Dev for MRM Care Team | Author | Not Started |  |  | 2021-05-21 |  | Sarah Taylor
System Integration Testing
Core Complete SIT for MRM Data Publication | Core | In Progress |  |  | 2021-05-14 |  | Devender Vidhani | 5/12: Sarah requested Core to provide demo 5/14.
Core Complete EXTQA Readiness for MRM Data Publication | Author | Not Started |  |  | 2021-05-24 |  | Sarah Taylor
Maven Wave Complete SIT for Care Team | Maven Wave | Not Started |  |  | 2021-05-26 | ~6/1/2021 | Dan Bouckeart | 5/11: Per Amita, for MW to start SIT testing they need Google to resolve issues with the HPDI tool. Once the issues are resolved, will have more concrete dates; hoping to resolve them this week.
Author Interop Complete SIT for Care Team | Author | Not Started |  |  | 2021-06-04 |  | Sarah Taylor
Author Complete End-to-End SIT | Author | Not Started |  |  | 2021-06-10 |  | Robert Spielberger | 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
User Acceptance Testing
Author Develop UAT Test Plan | Author | In Progress |  | 2021-04-15 | 2021-04-22 |  | Yuliya Roberts
Author Complete UAT for Care Team | Author | Not Started |  |  | TBD |  | Yuliya Roberts | 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
Allergies & Intolerance
Data Mapping
Author Provide Sample Data to Maven Wave | Author | Complete | 100% |  | 2021-03-15 | 2021-03-12 | Sarah Taylor | 3/12: Per Sarah, sample data & schema uploaded.
Maven Wave Complete Allergies Data Mapping | Maven Wave | In Progress |  |  | 2021-04-02 |  | Dan Bouckeart
Review Final Allergies Data Mapping | Maven Wave/Author | In Progress |  |  | 2021-05-04 |  | Jay Goebel/ Catherine Luttmer
Author Data Stewards Approve Final Data Mapping | Author | Not Started |  |  | 2021-05-05 |  | Karen Kinzel
Development
Core MRM Allergies Data Publication from CDF | Core | Complete | 100% |  | 2021-04-30 |  | Shivang Patel | 4/30: Core delivered Allergy MRM data publication to Dev. 4/23: CR-51 created for 6 addl MRM data publications & could affect current target date.
Maven Wave Complete Dev for Allergies | Maven Wave | Not Started |  |  | 2021-05-11 |  | Dan Bouckeart
Author Interop Complete Dev for Allergies | Author | Not Started |  |  | 2021-05-17 |  | Sarah Taylor | 5/3: Devender provided CR-51 delivery timeline [DEV Readiness 4/27, SIT Readiness 4/30, EXTQA Readiness 5/17, Targeted PROD Date 6/7]. [jrm] 4/27: As per Bala MRM (Allergies, CareTeams, Goals, NarrativeExtract (ClincalNotes), PlanCares, Problems, Procedures) - Dev complete by Sprint 3 (05/21) 4/23: James will provide date by EOD
System Integration Testing
Maven Wave Complete SIT for Allergies | Maven Wave | Not Started |  |  | 2021-05-26 | ~6/1/2021 | Dan Bouckeart | 5/11: Per Amita, for MW to start SIT testing they need Google to resolve issues with the HPDI tool. Once the issues are resolved, will have more concrete dates; hoping to resolve them this week.
Author Interop Complete SIT for Allergies | Author | Not Started |  |  | 2021-06-04 |  | Sarah Taylor | 4/23: James will provide date by EOD. [jrm] - 2 weeks from DEV complete is 6/4
Author Complete End-to-End SIT | Author | Not Started |  |  | 2021-06-10 |  | Robert Spielberger | 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
User Acceptance Testing
Author Develop UAT Test Plan | Author | Complete |  | 2021-04-15 | 2021-04-22 |  | Yuliya Roberts
Author Complete UAT for Allergies | Author | Not Started |  |  | TBD |  | Yuliya Roberts | 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
Clinical Notes [Narrative Extract]
Data Mapping
Author Provide Sample Data to Maven Wave | Author | Complete | 100% |  |  |  | Sarah Taylor
Maven Wave Complete Clinical Notes Data Mapping | Maven Wave | In Progress |  |  | 2021-05-05 |  | Dan Bouckeart
Review Final Clinical Notes Data Mapping | Maven Wave/Author | In Progress |  |  | 2021-05-06 |  | Jay Goebel/Catherine Luttmer
Author Data Stewards Approve Final Data Mapping | Author | Not Started |  |  | 2021-05-07 |  | Karen Kinzel
Development
Core MRM Clinical Notes Data Publication from CDF | Core | Not Started |  |  | TBD |  | Shivang Patel | 5/4: Shivang targeted 5/7 to provide delivery timeline.
Maven Wave Complete Dev for Clinical Notes | Maven Wave | Not Started |  |  | TBD |  | Dan Bouckeart
Author Interop Complete Dev for Clinical Notes | Author | Not Started |  |  | 2021-05-21 |  | Sarah Taylor | [jrm] 4/27: As per Bala MRM (Allergies, CareTeams, Goals, NarrativeExtract (ClincalNotes), PlanCares, Problems, Procedures) - Dev complete by Sprint 3 (05/21) 4/23: James will provide date by EOD
System Integration Testing
Maven Wave Complete SIT for Clinical Notes | Maven Wave | Not Started |  |  | TBD | ~6/1/2021 | Dan Bouckeart | 5/11: Per Amita, for MW to start SIT testing they need Google to resolve issues with the HPDI tool. Once the issues are resolved, will have more concrete dates; hoping to resolve them this week.
Author Interop Complete SIT for Clinical Notes | Author | Not Started |  |  | 2021-06-04 |  | Sarah Taylor | 4/23: James will provide date by EOD. [jrm] - 2 weeks from DEV complete is 6/4
Author Complete End-to-End SIT | Author | Not Started |  |  | 2021-06-10 |  | Robert Spielberger | 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
User Acceptance Testing
Author Develop UAT Test Plan | Author | In Progress |  | 2021-04-15 | 2021-04-22 |  | Yuliya Roberts
Author Complete UAT for Allergies | Author | Not Started |  | 2021-05-21 | 2021-06-10 |  | Yuliya Roberts | 5/6: UAT timeline Start Date 5/21 - End Date 6/10; functionality being delivered at different timeframes; testing soon as made available to team. 5/3: Overall Dev complete dates causing short window for E2E SIT & UAT timelines. Mitigation is to execute testing cycles either in parallel or partially sequenced. Meeting scheduled 5/5 to discuss plan.
Digital
Customized Developer Portal & Consent
Deploy Google HPDI Generic Developer Portal | Maven Wave | In Progress | ~ 60% | 2021-04-13 | 2021-05-14 |  | Dan Bouckeart | (see line 293 - date changed, but subtasks and deliverables have not changed)
Discover Org & Environment [Dev, Staging, Prod, etc.] | Maven Wave | Complete | 100% |  | 2021-04-19 |  | Daniel Ly
Deploy Generic Drupal Dev Portal to Humana Environment | Maven Wave | In Progress |  |  | 2021-04-29 | ~ 4/23/2021 | Shannon Rush | ETA of 4/23 communicated.
Sign-up for Dev Portal as Developer to Test | Maven Wave | Complete | 100% |  | 2021-04-13 |  | Daniel Ly
Test Overall Function of Dev Portal in Sandbox | Maven Wave | Complete | 100% |  | 2021-04-13 |  | Daniel Ly
Customize Portal w/Author Branding |  | In Progress | ~60% | 2021-04-02 | 2021-06-01
Design Guidance from Author Team | Author CXP | Complete | 100% | 2021-04-02 | 2021-05-03 | 2021-04-02 | CWS (UXD)
Design Review for Drupal Portal Author Branding | Maven Wave | In Progress |  | 2021-05-14 | `~5/14/2021 |  | Daniel Ly | Working Meeting ~5/7, URL to review ~ 5/12.
Business/Compliance Approval for Branding & Copy | Author CXP | In Progress |  | 2021-05-14 | 2021-06-01 |  | Business
Member Authentication & Consent |  | In Progress |  | 2021-04-12 | 2021-06-15
Consent API from Maven Wave/Google | Maven Wave | In Progress | ~ 45% |  | 2021-04-29 | ~5/3/2021 | Dan Ly/Daniel Bouckeart | (Available in lower environment for Author Eng). Might be able to move the Consent tech handoff forward a day or two. They understand that after 5/7 it will cause a delay on our end.
Author CXP Provide Member Consent Copy to MW | Author CXP | In Progress | ~ 45% | 2021-04-12 | 2021-04-29 | ~ 5/14/2021 | Erin Murphy/Carlene Marra | 5/10: Per Charles, in order to ensure we have something to provide branding/design guidelines for and see basic functionality, we've handed off draft copy to the vendor. Please note that there are compliance decisions needed for this consent piece that are still pending. (to reuse Humana's disclaimer/legal items or not). Carlene & Erin can share more, my understanding is that the Author final content needs input from Core. If we can get that this week, it would be helpful. While there is not an immediate impact and we can change content later, we said that after 5/14 it would be considered late. ETA unknown from Compliance - beginning escalation w/product & business.
Author Compliance Consent Approval | Author Compliance | Not started |  | 2021-05-14 | 2021-06-01 |  | Erin Murphy/Carlene Marra | 5/10: Erin asked Carlened if any update re: Privacy Policy and T&C’s for this feature. She was waiting to get a look at Core’s to determine if we could just link directly there or would need to tweak and build our own; waiting for Carlene to respond. ETA unknown from Compliance - beginning escalation w/product & business.
Author Interop Proxy Consent API | Author Interop | In Progress |  | 2021-05-12 | 2021-05-21 | ~6/4/2021 | Sarah Taylor/Shaliesh Soni | 5/12: Per Bala, team planning to complete before 1 week of Sprint 4; targeting 5/28. [jrm] 4/28: As per Bala, Consent API - Not yet slated to a sprint yet (plan bw Sprint 3/4) Added week of 4/19 - pending Approval of Sarah Taylor/Shaliesh Soni
Author CXP Build Ability to Revoke Member Consent | Author CXP | Not Started |  | 2021-06-06 | TBD | ~6/29/2021 | Fredrik Elvhede | PI7 Sprint 4 - SIT & UAT Start 5/29, SIT END 6/18, UAT END 6/18; OCR of 6/29 is estimated. DEPENDS ON INTEROP PROXY - which has been delayed from 5/21 to 5/28
Author - Compliance
Protected Information Review Council [PIRC]
Submit HPDI PIRC Request | Author | Complete | 100% |  |  | 2021-02-22 | Charles Southworth | PIRC Request ID # 2376
Present HPDI to PIRC Committee | Author | Complete | 100% |  |  | 2021-03-03 | Charles Southworth | HPDI PIRC approved; committee requested an architectural security review as part of approval.
Walkthrough of UX for Website | Author | Complete | 100% |  | 2021-03-23 |  | Charles Southworth
Review HPDI Architectural Security (CSAR) | Author | WIP |  | 2021-05-01 | 2021-05-21 |  | Aakash Sham | 4/14: Per Charles, review dependson getting infrastructure in place & blueprints set; changed target date to 5/1. 3/18: Per Charles, delayed due to training/team capacity; complete date TBD. 3/9: Charles asked PIRC committee to provide more details on what is needed for HPDI. Per Terry Perkins, want to ensure the new 'pieces' reviewed & communicating properly. Takes about 1-1 1/2 month to obtain approval. 5/10 - Updated to 5/21 based on feedback from Aakash. 5/11 - Intake request submitted to Core, content approved by Tim D. and Aakash S. (Changed Task owner to Aakash)
CMS Interoperability Requirements
Assign IT Owners for CMS/ONC/Metrics Tasks | Author | Complete | 100% |  | 2021-03-24 | 2021-03-22 | Helena Rawson | 3/22: Met & assigned DRIs to all CMS requirements Tasks [OQ-276 / OQ-277 / OQ-278]. 3/10: Sarah asked Compliance to notate more detailed action items for each task to assign appropriate owners.
Operational Readiness
Training
Submit Learning Request | Author | Complete |  |  | 2021-04-30 | 2021-04-27 | Ronald AngSiy | 4/27: Per Ronald, 1) Submitted a ticket, talked to David, met his team, and now coordinating w/Raquel on putting together care coordinator training material. 2) Will send Raquel screenshots when I can. Our compliance team is still waiting on Core for guidance/approval (whether we can use their compliance page and/or verbiage of our T&C page). 3) Once we get screenshots w/proper wording to Raquel, it takes 2-3 weeks to generate those education materials. 4/16: Informed Cynthia on Status Update call that Learning Request must be submitted to create the FAQ. 3/29 [Aisha]: Per Cynthia 3/26, an FAQ will need to be established for Care Coordinators & Provider Navigators. Any technical issues will be addressed through the Care Coordinator & Provider Navigator logging a SNOW ticket – which will be routed for research to the appropriate technical team (same process we follow for other technical issues today reported by members & providers on the website). 3/19 [Aisha]: Contacted David B. & Raquel M. regarding Training Tasks. Learning requests needs to be submitted before the team can start identifying Tasks.
Create FAQ Document | Author | Not Started |  |  | 2021-06-03 |  | Raquel Mitchell
Train Care Coordinators & Provider Navigators | Author | Not Started |  |  | 2021-06-17 |  | David Butch
Production Turn Activities
Core
Complete Rx EOB Production Turn Activities | Core | Complete | 100% |  | 2021-05-05 |  | Devender Vidhani | 5/10: Core turned MF1: Rx EOB to Prod but Author is not able to access. Per Ashley, Humana is trying to get some final approvals & actively working on it; will let Author know when complete.
Complete Drug Formulary Production Turn Activities | Core | In Progress | 75% |  | 2021-05-12 |  | Devender Vidhani | Includes MF4.
Complete Medications & Immunizations Production Turn Activities | Core | Not Started |  |  | 2021-05-25 |  | Devender Vidhani | Includes MF7 [CR-52].
Complete MRM Data Publications Production Turn Activities | Core | Not Started |  |  | 2021-06-07 |  | Devender Vidhani | Includes MF2 [CR-51]: Allergies, Care Team, Plan Cares, Problems, Procedures, Goals & Narrative Extract.
Complete MRM 6 Month Historic Load Production Turn Activities | Core | Not Started |  |  | TBD |  | Devender Vidhani | Includes MF6 [CR-51]: Prod date TBD.
Complete Provider & Pharmacy Directory Production Turn Activities | Core | Not Started |  |  | TBD |  | Devender Vidhani | Includes MF5; Prod date TBD.
Author
Sugar Complete Production Turn Activities | Sugar | Not Started |  |  | 2021-05-18 |  | Noel Winslow | 4/30: Per Noel, waiting for guidance but most likely 5/18.
Digital Complete Production Turn Activities | Author | Not Started |  |  | 2021-06-29 |  | Fredrick Elvhede | 5/12: Prod turn date changed from 6/15 to 6/29 due to timing of Interop Dev complete for Consent Revoke.
Interop Complete Production Turn Activities | Author | Not Started |  |  | 2021-06-22 |  | Sarah Taylor | 5/10: Per Sarah, confirm if Janie created Task in Jira. 5/3: Interop Prod date confirmed. 4/26: Tentative date; not yet confirmed.
Maven Wave
Maven Wave Complete Production Turn Activities | Maven Wave | Not Started |  |  | 2021-06-29 |  | Dan Bouckaert | 5/10: Per Amita, MW will have the code ready for Prod 6/29. 5/7: Confirming date w/MW.
UST
UST Complete Production Turn Activities | UST | Not Started |  |  | 2021-06-22 |  | Harris Bennetkurishingalcleetus | 5/6: Per Suresh, UST can turn the code to production on 6/22 if they receive UAT sign-off by 6/20. 4/28: Suresh meeting w/UST 5/3 to check if Prod date can be advanced. 4/26: Per Harris, Author needs to sign-off on UAT by 6/25 for UST to prepare for PROD deployment & execute it successfully by 7/1 go-live date. Includes CR-37 [Member Demographics, Coverage, PCP].