## Risks
RISKS
Risk No. | Date Identified | Reported By | Description | Probability | Impact | Preventative Actions | Contingent Actions | Mitigation Options | Owner | Actions By | Target Date | Status | Notes
1 | 2021-02-25 | Sarah Taylor | API for Pharmacy & Provider Directories: Assuming Author can proxy the Humana Core endpoint via Author Apigee portal. Author does not have a target date from Core on when this will be available to do a feasibility check to ensure the proxy will technically work. | [5 empty] | Devender Vidhani | Cille Kissel | TBD | Open | 3/8 [Charles]: Need commitment from Core on who is assigned to do the work.
2 | 2021-03-04 | Charles Southworth | Clinical Notes: Per Chris C., if we don't exclude, Author may end up with a people/process work effort that all existing Notes need to be cleaned up as a result or similar. Not sure what the volume is, but whatever it is will get bigger over time. | [5 empty] | Sarah Taylor | Helena Rawson | 2021-03-10 | Closed | 3/10 [Aisha]: Patrick Murta confirmed on Interoperability Discussion call w/Core Author should not expose Notes not deemed as Clinical.
3 | 2021-03-08 | Sarah Taylor | API for Drug Formulary: Assuming Author can proxy the Humana Core endpoint via Author Apigee portal. Author does not have a target date from Core on when this will be available to do a feasibility check to ensure the proxy will technically work. | [5 empty] | Devender Vidhani | Cille Kissel | TBD | Open | 3/8 [Charles]: Need commitment from Core on who is assigned to do the work.
4 | 3/1/-3/11/2021 | Charles Southworth | Identified scope of existing Google proposal did not include some of the work needed. | [5 empty] | Sarah Taylor | Bonnie Templin | 2021-03-19 | Open
5 | 2021-03-16 | Charles Southworth | UST has no funding to perform addl project work. | [5 empty] | Sarah Taylor | TBD |  | Open

## Actions
ACTIONS
Action No: | Date Raised | Area | Priority | Description | Action By | Deadline | Progress | Status
1 | 2021-03-10 | Data Subject | High | Health Edge was planning to work through the Member Demographic & Coverage Data Subjects as priority to support HPDI initiative. | Sarah Taylor | 2021-03-15 | 3/10 [Aisha]: Sarah sent follow-up email asking when data will be available for review. 3/4: Abhi sent follow-up email asking for update. 2/24: HE/Humana follow-up Compliance meeting held and HE agreed to extract data. | Pending
2 | 2021-03-10 | Project Scope | High | Requested Google to adjust the scope of Phase 2 to include addl effort; resulting in likely cost increase for the project. | Sarah Taylor |  | 3/11: Waiting for Google to send new Phase 2 proposal. | Pending
3 | 2021-03-16 | Membership | High | Follow-up w/DK to obtain UST estimate to build the membership data publication | James Minks |  |  | Pending

## Issues
Issues
Issue No. | Priority | Description | Owner | Cause | Resolution | Status | Comments | Target Date

## Decisions
Decisions
Decision No: | Date Opened | Raised By | Description | Category | Status | Clarification | Approver/Decision Maker | Date Closed | Channel | Notes
1 | 2021-02-18 | Sarah Taylor | The claims data topic is the existing data exchange that UST has built to publish claims data out for Humana Core to consume. | System of Record | Closed | Leverage the existing claims data topic to meet HDPI requirements. | Nikki Woodcox | 2021-02-25 | Teams Chat
2 |  | Sarah Taylor | Smoking Status: We do not believe this data is maintained by Author. It appears to come as part of an antiquated system and we are specifically forbidden from gathering this data from members during intake. | Compliance | Pending | Author not obligated to release smoking status if the information was part of a previous plan. | Helena Rawson |  | Meeting | 3/12 [Aisha]: Helena does not want Smoking Status excluded from scope since it is a required Data Subject. However, it should be identified in the 3/11 [Aisha]: Charles sent email to Helena requesting approval to remove Smoking Status from scope. 3/10 [Aisha]: Patrick Murta confirmed on Interoperability Discussion call w/Core Author not obligated to release smoking status if the information was part of a previous plan. Per Sarah, CI eligibility file identified 5 members w/Smoking Status; assume information was part of a previous plan. Author does not capture smoking status and it is not a question on Author HRA.
3 |  | Sarah Taylor | Determine if data should be loaded as 'batch' or 'on demand'? | Tech | Closed | Author intends to use multiple formats. New Scope to be added to the Google contract as a result. | Sumana Bellary/Sarah Taylor | 2021-03-10 | Meeting | Sumana & Sarah proposed and approved this approach in several meetings with Google between 3/6 & 3/10.
4 | 2021-02-25 | Sarah Taylor | What is the source for member data? | System of Record | Closed | HRDW will be used as the source for member data. | Sarah Taylor | 2021-02-25 | Teams Chat
5 |  | Sarah Taylor | Is a VSR needed for Core? |  | Open |  | Sarah Taylor |  | Email | 3/10 [Aisha]: Emailed VSR v3 to Chris & Pam for review/approval. 3/9 [Aisha]: Business approval needed; Sarah sent VSR to Pam & Chris.
6 | 2021-02-20 | Sarah Taylor | Core is deriving this info from claims data but suspect we want to leverage OML to meet this requirement. I am not clear on exactly why core is not using OML but can try to poke and prod for more info. Are we all aligned that Author will proceed with using OML to meet this requirement or do we need to have additional discussions to make the decision final? | System of Record | Closed | Author will use OML. | Pam Bell | 2021-02-25 | Email
7 | 2021-03-04 | Sarah Taylor | Health Concerns vs Problems: What we have captured in Sugar is closer aligned to the definition for 'Health Concerns' data subject rather than 'Problems'. | Compliance | Pending | Author does not need to include Problems since it is not codifiable in an accepted format. | Helena Rawson | 2021-03-10 | Meeting | 3/11 [Aisha]: Charles sent email to Helena requesting approval to remove Problems from scope. 3/10 [Aisha]: Patrick Murta confirmed on Interoperability Discussion call w/Core Author does not need to include Problems since it is not codifiable in an accepted format.
8 | 2021-03-04 | Sarah Taylor | Clinical Notes: We currently capture notes in Sugar but they were never intended to be exposed to patients. Author does not receive Clinical Notes from Claims. Our request is we do not categorize these as Clinical Notes and not expose as part of HPDI initiative. | Compliance | Pending | Author should not expose Notes not deemed as Clinical. | Helena Rawson |  | Meeting | 3/11 [Aisha]: Charles sent email to Helena requesting approval to remove Clinical Notes from scope. 3/10 [Aisha]: Patrick Murta confirmed on Interoperability Discussion call w/Core Author should not expose Notes not deemed as Clinical.
9 | 2021-03-09 | Tim Doyle | Member identifier is entity ID and Author will provide member card ID on the coverage level. | System of Record | Closed | This is a better member indentifier than using membGenKey. | Tim Doyle
10 | 2021-03-09 | Sarah Taylor | Need an architecture recommendation from Mavenwave on how we handle merging data from two sources, systems into the FHIR store. | Tech | Open | Maven Wave is the recommender. | Sumana Bellary
11 | 2021-03-10 | Patrick Murta | Author should not send data from a previous plan [pre-Author]. | Compliance | Closed | Core is the expert and shared this approach. | Patrick Murta/Helena Rawson | 2021-03-10 | Meeting | 3/10 [Aisha]: Patrick Murta confirmed on Interoperability Discussion call w/Core Author not obligated to release information that was part of a previous plan.

## Dropdowns
Dropdowns
To change menu items simply edit the Menu and Description fields below.
Actions
Field | Menu | Description
Priority | High | Complete in 1 - 2 days
| Medium | Complete in 1 week
| Low | Complete in 1 to 2 weeks
Status | Open | In progress
| Pending | Waiting on action by another party
| Resolved | Resolved pending agreement from customer/sponsor
| Closed | Closed as agreed by customer/sponsor
Risks
Field | Menu | Description
Probability | High | Very likely that this risk will occur/happen.
| Medium | 50/50 chance that this risk will occur.
| Low | Low probability that this risk will occur.
Impact | High | This would badly impact the project e.g. cost, delay, quality.
| Medium | A manageable impact on the project.
| Low | A low impact on the project.
Status | Open | In progress
| Pending | Waiting on action by another party
| Closed | Closed as agreed by customer/sponsor
Issues
Field | Menu | Description
Priority | High | This issue must be resolved for progress to be made.
| Medium | This impacts the project, but doesn’t stop progress.
| Low | A low impact on the project. Perhaps optional to fix.
Status | Open | In progress
| Pending | Waiting on action by another party
| Resolved | Resolved pending agreement from customer/sponsor
| Closed | Closed as agreed by customer/sponsor