## Sheet1 (hidden)
Feature No. | Features | Dependancies | Sprint 1 ( End Date: 9/4) | Sprint 2 ( End Date: 9/18) | Sprint 3 ( End Date: 10/2) | Sprint 4 ( End Date: 10/16) | Sprint 5 ( End Date: 10/30)
1698 | CMS2 Data Exchange |  |  | 1.Hospice - 9/11 2.CSP monthly full file - 9/18 3.MSPCOBMA - 9/18 4. Credible Coverage - 9/18 5. COBD - 9/18 6. CSP Daily Delta - 9/18
1713 | Historical Auth Data Exchange | CDF, Humana Core |  | 1.Auth Data Feed (9/11) 2.Attachments ( 9/18) 3.Medical Code ( 9/18) 4.QIO Appeals ( 9/18) 5.Clinical Review ( 9/18) 6.MD Review ( 9/18) |  |  |  | CDF and Interop same sprint end
1712 | ADT Alerts | CDF, Humana Core |  |  |  | Admission, Discharge and Transfers: Published to UST |  | CDF done with ADT last PI Sprint 4 for Interop
1743 | Document Management |  | Allow Upload and Search of Paper Claims using Doc Control Number | Allow ACK/NACK for CRE ( Humana Documents) & Innovare (G&A Docs) systems. Allow CRE to publish documents to EDGE | Document API: Publish G&A documents to Innovaare. Document API: Allow for Prior Auth Letter association to EOC through Document API: Support Member and provider document as well as Reference ID searches. Document Repo: Accept Member Card ID, Case ID, Core Document ID in attribute list. |  | Document Management integration with CRE service for misroutes
1761 | POA API |  |  | POA API : Published to APIGEE
1686 | Proxy ID Card - Reorder ID Card |  |  | View ID Card Status : Published to APIGEE | Order ID Card : Published to APIGEE
1696 | Proxy One Medication List,Mail Order Prescription and Over the Counter |  | OML: Publish APIGEE proxy MOP: Publish APIGEE proxy OTC: Publish APIGEE proxy for Order Submit and Details | Pharmacy Claims: Published to APIGEE Pharmacy Claim Details: Published to APIGEE | OTC Allowance: Published to APIGEE OTC Balance: Published to APIGEE
1151 | Automate file pickup for Carrington and Eyemed - Directory data |  |  |  | Automate Carrington SFTP Pick Automate Eyemed SFTP File Pick
1775 | MRM Enhancements | Humana Core, CDF |  |  |  | 1. Create Tasks in Innovare Task 2.Accommodate MRM Publication Enhancements
1722 | Claims Recon, Membership Recon and Claims Payment Recon | Humana Core, CDF |  |  |  | CDF: Claims Recon ( Monthly) Member Recon ( Monthly) Auth Recon Claims Payment |  |  | CDF and Interop done Sprint 4
1765 | Claims API and Auth API enhancments Pharmacy Claims integration | UST |  | Member Medical Accums: Publish to APIGEE | Claims Summary - Publish to APIGEE | Auth Details & Summary: Publish to APIGEE G&A Case ID Details: Publish to APIGEE Claims Details: Publish to APIGEE | G&A Case Summary: Publish to APIGEE
1323 | Update PCP Get and Update preferences |  |  | Preferences Published to UST | Get Preferences: Publish to APIGEE Update PCP: Publish to APIGEE |  | Update Preferences: Publish to APIGEE |  | CDF and Interop done in Sprint 2
718 | Provider Demographic Exchange | Humaan Core, CDF |  |  |  | Provider Demographics, Contracts and Networks: Published to UST |  |  | CDF finishes sprint 2 Interop finishes sprint 4
1702 | Provider Entity Ingestion & Provider data publication to Sugar | UST |  |  |  | Providers in Nexus & Published to Sugar |  |  | UST Publication Sprint 4 Interop in sprint 3 or 4
1754 | Nexus: Care Co ordinators association to Members |  |  | Associate Entity Ingestion | Create Relationship between Members and Care Coordinators. Nexus to BigQuery Integration
1807 | Exchange Anvita, Clinical Insights and DH&A Model Files | [5 empty] | Analytics files available in ADF ( 10/25) |  | CDF can have Anvita available earlier Interop done sprint 4
717 | Payment Data (CDF only) |  |  |  |  | Oracle AP Payments: Data Exchanged
1806 | IXIT Data transfer | [5 empty] | IXIT Data exchange: Published to HRP |  | Interop Done: Sprint 2 CDF Done: Sprint 5

## PI8
Feature No. | Feature | PI8 Sprint 1 (End Date: 7/2) | PI8 Sprint 2 (End Date: 7/16) | PI8 Sprint 3 (End Date: 7/30) | PI8 Sprint 4 (End Date: 8/13) | PI8 Sprint 5 (End Date: 8/27) | Notes
EPI-2567 | Enhance Claims Pricing service (ie CIS Bridge) to call new rest API |  | Proxy new CIS Bridge rest API
EPI-2628 | Move batch files for Operations to access to internal file share location |  | Update error reports with business reasons and provide manually: -Claims -Membership Drop error reports for the following data exchanges to internal file share
EPI-2627 | Provide CMS indicators to Sugar team to display on UX screens | Provide the CMS indicators and history for: -ESRD -Hospice -Cost Share Protection -Coordination of Benefits -LIS |  |  |  |  | 7/7--in SIT as of today and need to determine if we are using HRDW replica for prod
EPI-2632 | Proxy the par/non-par API from HRCM so Sugar can consume |  | Proxy Provider Profile-Par, Non-Par API from HRCM endpoint
EPI-2568 | Doc API to provide auth outcome letters for member portal to display |  | Modify existing Download Doc endpoint to include auth outcome
EPI-2588 | Provide Drug Image API to contact center dev team to display on Sugar portal |  | Pharmacy - Drug Images (FDB) API Pharmacy - Drug Image (FDB) API - Image firestore
EPI-2395 | Shift ownership of UST APIs to internal dev team
EPI-2786 | Provide capability for POD data to be ingested to Nexus and surfaced to Sugar via relationship API
EPI-1557 | Retrofit Provider Dir and Pharmacy APIs with WebCore
EPI-2745 | Analysis of Nexus to ensure it is resilient, scalable and sustainable
EPI-2588 | Pharmacy API work for PI8: Proxy Drug Image API and enhance OML/PA endpoints
EPI-2777 | Webcore MVP-Folder Structure
EPI-2778 | Webcore MVP-Use BaseStartup/ihost creation
EPI-2779 | Webcore MVP-Model Validation
EPI-2780 | Webcore MVP-REST Client for HTTP requests